## Sheet1
IFSC-MICR CODES- All Banks
VERSION NO : TESTED BY : ANITHA. P |  |  |  | VERIFIED BY : DATE : 13/03/2023
SPLASH PAGE
TEST ID | TEST DESCRIPTION | TEST PROCEDURE | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS
BANK_SPLASH_01 | Check whether the splash page displays the logo | 1.Open application 2.Check the logo |  | The splash page should display the logo | The splash page displays the logo | PASS
BANK_SPLASH_02 | Check whether the the logo is static | 1.Open the application 2. check the logo |  | The logo should be static | The logo is static | PASS
BANK_SPLASH_03 | Check whether the logo should be clear | 1.Open the application 2. check the logo |  | The logo should be clearly visible | The logo is clear | PASS
BANK_SPLASH_04 | Check whether the logo is properly aligned | 1.Open application 2.Check the logo |  | The logo should be properly aligned | The logo is properly alignrd | PASS
BANK_SPLASH_05 | Check whether the logo remains there for a long time | 1.Open the application |  | The logo display time should be of few seconds | The logo displays only for few seconds | PASS
BANK_SPLASH_06 | Check whether there is no spelling mistake in the SPLASH PAGE | 1.Open the application |  | There should be no spelling mistake in the SPLASH PAGE | There is no spelling mistake in the SPLASH PAGE | PASS

## Sheet2
ALL BANKS PAGE
TEST ID | TEST DESCRIPTION | TEST PROCEDURE | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS
BANK_ALLBANK_01 | Check whether the list of banks page is loaded after the splash page | 1. Open the application 2.Check for 'All Banks Page' |  | The 'All Banks Page' should be loaded. | The 'All Banks Page' is loaded successfully. | PASS
BANK_ALLBANK_02 | Check whether the list of banks are displayed in the alphabetical order | 1. Open the application 2.Check the list of banks |  | The names of banks should be arranged in the alphabetical order | The names of banks are arranged in the alphabetical order | PASS
BANK_ALLBANK_03 | Check whether the page can be scrolled up and down to view the whole list | 1. Open the application 2.Check for the whole list of banks |  | The page could be scrolled up and down. | The page is being scrolled up and down successfully. | PASS
BANK_ALLBANK_04 | check whether the selection of a bank leads to the bank details page. | 1.Open the application 2. Select a bank |  | The selection of a bank should redirects to the bank details page. | The selection of a bank redirects to the Bank Details page successfully. | PASS
BANK_ALLBANK_05 | Check whether the links for IFSC, MICR, RECENTS, FAVOURITES are present. | 1. Open the application 2.Check for the links |  | The links for IFSC, MICR, RECENTS and FAVOURITE should be there in the page. | The links for IFSC, MICR, RECENTS and FAVOURITES are displayed in the page. | PASS
BANK_ALLBANK_06 | Check whether there is a search field in the page | 1.Open the application 2. Check for the 'Search' field |  | There should be a search field in the page. | The 'Search' field is there in the page. | PASS
BANK_ALLBANK_07 | Check whether there is any spelling mistkes in the page. | 1.Open the application 2. Check the spelling |  | There should be no spelling mistake in the page | There is no spelling mistake in the page | PASS
BANK_ALLBANK_08 | Check whether the click on 'Recents' link redirects to new page | 1.OPen the application 2. Click on the 'Recents' link |  | Clicking on the 'Recents' link should redirects to a new page. | Clicking on the 'Recents' link is redirected to a new page | PASS
BANK_ALLBANK_09 | Check whether the click on 'IFSC' link redirects to new page | 1.Open the application 2. Click on the 'IFSC' link |  | Clicking on the 'IFSC' link should redirects to a new page. | Clicking on the 'IFSC' link is redirected to a new page | PASS
BANK_ALLBANK_10 | Check whether the click on 'MICR' link redirects to new page | 1.Open the application 2. Click on the 'MICR' link |  | Clicking on the 'MICR' link should redirects to a new page. | Clicking on the 'MICR' link is redirected to a new page | PASS
BANK_ALLBANK_11 | Check whether the click on 'Favourites' link redirects to new page | 1.Open the application 2. Click on the 'Favourites' link |  | Clicking on the 'Favourites' link should redirects to a new page containing the list of banks those were added as favourites | Clicking on the 'Favourites' link has been redirected to a new page containing the list of banks those were added as favourites | PASS
BANK_ALLBANK_12 | Check whether a blinking cursor will appear while clicking on the Search field | 1. Open the application 2. Click on the 'Search' field |  | A blinking cursor should appear while clicking on the Search field | A blinking cursor is appeared while clicking on the Search field | PASS
BANK_ALLBANK_13 | Check whether banks can be searched | 1. Open the application 2. Type the name of abank in the Search field | SBI | The name of the bank should be displayed after searchig | The name of bank is displayed successfully | PASS
BANK_ALLBANK_14 | Check whether the 'Search ' field allow to enter numbers | 1. Open the application 2. Enter numbers in the Search field | 123 | The 'Search' field should not accept any numbers and should display an error message | The 'Search ' field acepts numbers and do not display any error message | FAIL
BANK_ALLBANK_15 | Chek whether the 'Search ' field accepts special characters | 1. Open the application 2. Enter special characters in the Search field | @# | The 'Search' field should not accept any special characters and should display an error message | The 'Search ' field acepts special characters and do not display any error message | FAIL
BANK_ALLBANK_16 | Check whether searching of a bank that is not in the list of banks should display an error message | 1. Open the application 2. Enter some letters in the Search field | assaa | An error message should be displayed | No error message is displayed | FAIL

## Sheet3
STATE LIST PAGE
TEST ID | TEST DESCRIPTION | TEST PROCEDURE | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS
BANK_STATELIST_01 | Check whether the selection of a bank displays the list of states having the branches. | 1.Open the application 2. Select any bank 3. check for the list of states |  | The list of states should be displayed | The list of states is displayed successfully. | PASS
BANK_STATELIST_02 | Check whether the selection of a state leads to a new page | 1.Open the application 2. Select any bank 3. Select a state |  | Selection of a state should redirects to new page | Selection of a state is redirected to a new page | PASS
BANK_STATELIST_03 | Check whether there is a search field for searching the states | 1.Open the application 2. Select any bank 3. Select a state 4. Checkfor the search field |  | There should be search field inthe 'State List' page | A search field is there in the 'State List' page | PASS
BANK_STATELIST_04 | Check whether cursor is blinking on the search field while clicking on the 'Search Field' | 1.Open the application 2. Select any bank 3. Click on the search field |  | A cursor should blink in the search field while clicking on it | A cursor is blinking while clicking on the search field | PASS
BANK_STATELIST_05 | Check whether we can type in the 'Search' field | 1.Open the application 2. Select any bank 3. Type in the Search field |  | We could type in the 'Search' field | Typed in the 'Search' field successfully | PASS
BANK_STATELIST_06 | Check whether states can be searched from the list of states displayed | 1.Open the application 2. Select any bank 3. Type in the Search field | kerala | Should display the state from the list of states | The state is displayed successfully | PASS
BANK_STATELIST_07 | Check whether the 'Search ' field allow to enter numbers | 1.Open the application 2. Select any bank 3. Type numbers in the Search field | 123 | The 'Search' field should not allow to enter any numbers and should display an error message | The 'Search ' field acepts numbers and do not display any error message | FAIL
BANK_STATELIST_08 | Check whether the 'Search ' field allows to enter special characters | 1.Open the application 2. Select any bank 3. Type special characters in the Search field | @# | The 'Search' field should not allow to enter any special characters and should display an error message | The 'Search ' field allows to enter special characters and do not display any error message | FAIL
BANK_STATELIST_09 | Check whether searching a state that is not in the list of states should display an error message | 1.Open the application 2. Select any bank 3. Type a state that is not in the list of states displayed | qqwss | An error message should be displayed | No error message is displayed | FAIL

## Sheet4
DISTRICT LIST PAGE
TEST ID | TEST DESCRIPTION | TEST PROCEDURE | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS
BANK_DISTRICT_01 | Check whether the selection of a state displays the list of districts where the branches are located | 1.Open the application 2. Select any bank 3. Select a state | kerala | The selection of a state should display the list of districts where branches of tha selected bank are located | The list of districts are displayed successfuly | PASS
BANK_DISTRICT_02 | Check whether the selection of a district displays the list of branches in the particluar district | 1.Open the application 2. Select any bank 3. Select a state 4. Select a district | kerala--> kollam | The selection of a district should display the list of branches | The list of branches is displayed successfully | PASS
BANK_DISTRICT_03 | Check whether cursor is blinking on the search field while clicking on the 'Search Field' | 1.Open the application 2. Select any bank 3. Select a state 4. Click on the search field |  | A cursor should blink in the search field while clicking on it | A cursor is blinking while clicking on the search field | PASS
BANK_DISTRICT_04 | Check whether we can type in the 'Search' field | 1.Open the application 2. Select any bank 3.Select state 4. Type in the Search field | kollam | We could type in the 'Search' field | Typed in the 'Search' field successfully | PASS
BANK_DISTRICT_05 | Check whether districts can be searched from the list of districts displayed | 1.Open the application 2. Select any bank 3.Select state 4. Type in the Search field |  | Should display the state from the list of districts | The districts is displayed successfully | PASS
BANK_DISTRICT_06 | Check whether the district 'Search ' field allows to enter numbers | 1.Open the application 2. Select any bank 3. Select a state 4. Type numbers in the Search field | 123 | The 'Search' field should not accept any numbers and should display an error message | The 'Search ' field acepts numbers and do not display any error message | FAIL
BANK_DISTRICT_07 | Chek whether the district 'Search ' field accepts special characters | 1.Open the application 2. Select any bank 3. Select a state 4. Type special characters in the Search field | @# | The 'Search' field should not accept any special characters and should display an error message | The 'Search ' field acepts special characters and do not display any error message | FAIL
BANK_DISTRICT_08 | Check whether searching a district that is not in the list of districts should display an error message | 1.Open the application 2. Select any bank 3.Select a state 4. Type a district name that is not in the displayed list of districts |  | An error message should be displayed | No error message is displayed | FAIL
BANK_DISTRICT_09 | Check whether the district displayed is belongs to the state which already selected | 1.Open the application 2. Select any bank 3.Select a state 4. check the displayed district list |  | The districts should belongs to the state which already selected | Some districts are not belongs to the seleted state | FAIL

## Sheet5
BRANCH PAGE
TEST ID | TEST DESCRIPTION | TEST PROCEDURE | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS
BANK_BRANCH_01 | Check whether the selection of a branch displays the details of the bank | 1. Open the application 2. Select any bank 3. Select a state 4. Select a district 5. Select a branch | SBI -->kerala -->Alappuzha --> kayamkulam | The selection of a branch should display the details of the bank | The details of the bank is displayed successfully | PASS
BANK_BRANCH_02 | Check whether there is a Search field in the Branch Page | 1. Open the application 2. Select any bank 3. Select a state 4. Check for Search fields |  | There should be Search field in the Branch Page | The Search field is there in the Branch Page | PASS
BANK_BRANCH_03 | Check whether the Search field allow to search for a branch | 1. Open the application 2. Select a bank 3. Select a state 4. Select district 5. Search a branch |  | Could search a branch and display the bank details | The Searching for a branch have done successfully | PASS
BANK_BRANCH_04 | Check whether the brach 'Search ' field allow to enter numbers | 1.Open the application 2. Select a bank 3.Select a state 4.Select district 5. Enter numbers in the search field | 123 | The 'Search' field should not allow to enter any numbers and should display an error message | The 'Search ' field allow to enter numbers and do not display any error message | FAIL
BANK_BRANCH_05 | Check whether the branch 'Search ' field allow to enter special characters | 1.Open the application 2. Select a bank 3.Select a state 4.Select district 5. Enter special characters in the search field | @# | The 'Search' field should not allow to enter any special characters and should display an error message | The 'Search ' field allow to enter special characters and do not display any error message | FAIL
BANK_BRANCH_06 | Check whether searching a branch that is not in the list of branches should display an error message | 1.Open the application 2. Select a bank 3.Select a state 4.Select district 5. Enter a branch in the list of branches | ass | An error message should be displayed | No error message is displayed | FAIL

## Sheet6
BANK DETAILS PAGE
TEST ID | TEST DESCRIPTION | TEST PROCEDURE | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS
BANK_BNKDTLS_01 | Check whether the bank details page is displayed when a branch is selected | 1. Open the application 2. Select any bank --> state --> district --> branch |  | Should display the details of the bank | The details of bank is displayed successfully | PASS
BANK_BNKDTLS_02 | Check whether there is no spelling mistakes | 1. Open the application 2. Select any bank --> state --> district --> branch |  | Should not be any spelling mistakes | There is no spelling mistakes int the page | PASS
BANK_BNKDTLS_03 | Check whether the bank details can not be edited | 1. Open the application 2. Select any bank --> state --> district --> branch 3.Check the details |  | The details should not be edited | The details can not be edited | PASS
BANK_BNKDTLS_04 | Check whether the zip code is correct | 1. Open the application 2. Select any bank --> state --> district --> branch 3. Check the zip code |  | The zip code should be correct | The zip codes of some banks are not correct | FAIL
BANK_BNKDTLS_05 | Check whether the addresses are correct | 1. Open the application 2. Select any bank --> state --> district --> branch 3. Check the address |  | The address should be correct | The address of some banks are not correct | FAIL
BANK_BNKDTLS_06 | Check whether the IFSC Code and MICR Code are included in the details | 1. Open the application 2. Select any bank --> state --> district --> branch 3. Check IFSC Code and MICR Code |  | The IFSC Code and MICR Code should included in the details | The IFSC Code and MICR Code are included in the details | PASS
BANK_BNKDTLS_07 | Check whether there are buttons for Share bank details and Add to favourites | 1. Open the application 2. Select any bank --> state --> district --> branch 3.Check the buttons |  | The 'Share Bank Detail' button and 'Add To Favourites' buttons should be there in the page | The 'Share Bank Detail' button and 'Add To Favourites' buttons is there in the page | PASS
BANK_BNKDTLS_08 | Check whether a new window of locations is displayed to which the details to be shared while clicking on the 'Share Details' button | 1. Open the application 2. Select any bank --> state --> district --> branch 3.Click on 'Share Bank Details' button |  | Should display a new window of destination location | A new window of destination locatios is displayed | PASS
BANK_BNKDTLS_09 | Check whether sharing is done while clicking on the 'Share Bank Details' button | 1. Open the application 2. Select any bank --> state --> district --> branch 3.Click on 'Share Bank Details' button |  | Should share the details to the selected destination | The details are shared successfully | PASS
BANK_BNKDTLS_10 | Check whether the selected bankis added to the list of favourites while clicking on the 'Add To Favourites' button | 1. Open the application 2. Select any bank --> state --> district --> branch 3.Click on 'Add To Favourites' button |  | The selected bank should added to the 'Favourite' and should display a message | The selected bank is added to the list of Favourites and displayed the successfully added message | PASS
BANK_BNKDTLS_11 | Check whether the label of 'Add To Favourites' button hass changed to 'Remove From Favourites' after adding the selected bank to the favourites | 1. Open the application 2. Select any bank --> state --> district --> branch 3.Click on 'Add To Favourites' button |  | The button label should changed to 'Remove From Favourites' | The button label has changed to "Remove From Favourites' | PASS
BANK_BNKDTLS_12 | Check whether the 'Remove from Favourites' button removes the bank from the list of favourites | 1. Open the application 2. Select any bank --> state --> district --> branch 3.Click on 'Add To Favourites' button 4. Click on the 'Remove From Favourites' button |  | The clicking of 'Remove From Favourites ' button should remove the selected bank from the list of favourites and should display a message | The clicking of 'Remove From Favourites ' button has removed the selected bank from the list of favourites and displayed a message | PASS
BANK_BNKDTLS_13 | Check whether the label of 'Remove From Favourites' button hass changed to 'Add To Favourites' after removing the selected bank from the list of favourites | 1. Open the application 2. Select any bank --> state --> district --> branch 3.Click on 'Add To Favourites' button 4. Click on the 'Remove From Favourites' button |  | The button label should changed to 'Add To Favourites' | The button label has changed to "Add To Favourites' | PASS

## Sheet7
RECENTS PAGE
TEST ID | TEST DESCRIPTION | TEST PROCEDURE | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS
BANK_RECENTS_01 | Check whether clicking of 'Recents' link redirects to a page containing list of banks that has been searched recently | 1.OPen the application 2. Click on the 'Recents' link |  | The clicking of 'Recents' link should have display the list of recently searched banks | The clicking of 'Recents' has displayed the list of recently searched banks | PASS
BANK_RECENTS_02 | Check whether the last searched bank is at the top of the list | 1.OPen the application 2. Click on the 'Recents' link 3.Check the list |  | The last searched bank should be at the top of the list | Te last searched bank is at the top of the list | PASS
BANK_RECENTS_03 | Check whether the selection of a bank from 'Recents' is displaying the details of the bank | 1.OPen the application 2. Click on the 'Recents' link 3. Select a bank |  | The selection of bank should display the details of the bank | The selection of bank is displaying the details of the bank | PASS
BANK_RECENTS_04 | Check whether there is an option to clear the search history | 1.OPen the application 2. Click on the 'Recents' link 3. Check for clear button |  | There should be an option for clearing the seach history | There is no option to clear the history | FAIL

## Sheet8
IFSC SEARCH
TEST ID | TEST DESCRIPTION | TEST PROCEDURE | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS
BANK_IFSCSEARCH_01 | Check whether the clicking on IFSC link is displaying a search field to search the IFSC code | 1.Open the application 2. Click on the link 'IFSC' |  | Search field should be displayed while clicking on the 'IFSC' link | Search field is displayed when click on the 'IFSC' link | PASS
BANK_IFSCSEARCH_02 | Check whether a suggestion list of IFSC code is displayed while typing on the Search field | 1.Open the application 2. Click on the link 'IFSC' 3. Type in the Search field |  | A suggestion list of IFSC code should be displayed while typing on the Search field | A suggestion list of IFSC code is displayed while typing on the Search field | PASS
BANK_IFSCSEARCH_03 | Check whether bank details is displayed while searching the 'IFSC code' | 1.Open the application 2. Click on the link 'IFSC' 3. Enter IFSC code in the Search field | SBIN0000024 | The corresponding bank details should be displayed whille searching the IFSC code | The corresponding bank details is displayed whille searching the IFSC code | PASS
BANK_IFSCSEARCH_04 | Check whether the search field allow to enter only alphabets | 1.Open the application 2. Click on the link 'IFSC' 3. Enter only alphabets in the Search field | sbiiibiqqq | The IFSC Search field should not allow to enter alphabets only and should display an error message | The IFSC Search field is allowing to enter alphabets only and it does not displaying any error message | FAIL
BANK_IFSCSEARCH_05 | Check whether the Search field allow to enter more than 11 alphanumeric charactres | 1.Open the application 2. Click on the link 'IFSC' 3. Enter more than 11 characters in the Search field | sbin000002345 | The Search field Should not allow to enter more than 11 alphanumeric characters and should display the error message | More than 11 alphanumeric characters are allowed to enter and it does not displaying any error message | FAIL
BANK_IFSCSEARCH_06 | Check whether the Search field accepts less than 11 alphanumeric charactres | 1.Open the application 2. Click on the link 'IFSC' 3. Enter less than 11 characters in the Search field | sbi11 | The Search field Should not accept less than 11 alphanumeric charactersand should display the error message | Less than 11 alphanumeric characters are allowed to enter and it does not displaying any error message | FAIL
BANK_IFSCSEARCH_07 | Check whether the Search field allow to enter space | 1.Open the application 2. Click on the link 'IFSC' 3. Enter IFSC code with space | sbin00. 000 | The search field should not allow to enter white space and should display an error message | The search field allow to enter white space and does not displaying any error message | FAIL
BANK_IFSCSEARCH_08 | Check whether the 'Search ' field allow to enter any special characters | 1. Open the application 2. Enter special characters in the Search field | @# | The 'Search' field should not allow to enter any special characters and should display an error message | The 'Search ' field allow to enter special characters and it does not display any error message | FAIL
BANK_IFSCSEARCH_09 | Check whether the search field allow to enter only numbers | 1.Open the application 2. Click on the link 'IFSC' 3. Enter only numbers in the Search field | 34566778876 | The IFSC Search field should not allow to enter numbers only and should display an error message | The IFSC Search field allows to enter only numbers and it does not displaying any error message | FAIL

## Sheet9
MICR SEARCH PAGE
TEST ID | TEST DESCRIPTION | TEST PROCEDURE | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS
BANK_MICRSRCH_01 | Check whether the clicking on 'MICR' link is displaying a search field to search the MICR code | 1.Open the application 2. Click on the link 'MICR' |  | Search field should be displayed while clicking on the 'MICR' link | Search field is displayed when click on the 'MICR' link | PASS
BANK_MICRSRCH_02 | Check whether a suggestion list of MICR code is displayed while typing on the Search field | 1.Open the application 2. Click on the link 'MICR' 3. Type in the Search field |  | A suggestion list of MICR code should be displayed while typing on the Search field | A suggestion list of MICR code is displayed while typing on the Search field | PASS
BANK_MICRSRCH_03 | Check whether bank details is displayed while searching the 'MICR code' | 1.Open the application 2. Click on the link 'MICR' 3. Enter MICR code in the Search field | 110002001 | The corresponding bank details should be displayed whille searching the MICR code | The corresponding bank details is displayed whille searching the MICR code | PASS
BANK_MICRSRCH_04 | Check whether the MICR search field allow to enter alphabets | 1.Open the application 2. Click on the link 'MICR' 3. Enter alphabets in the Search field | sbiiibiqqq | The 'MICR' Search field should not allow to enter alphabets and should display an error message | The MICR Search field is allowing to enter alphabets and it does not displaying any error message | FAIL
BANK_MICRSRCH_05 | Check whether the 'Search ' field allow to enter any special characters | 1. Open the application 2. Enter special characters in the Search field | @# | The 'Search' field should not allow to enter any special characters and should display an error message | The 'Search ' field allow to enter special characters and it does not display any error message | FAIL
BANK_MICRSRCH_06 | Check whether the Search field allow to enter more than 9 digits | 1.Open the application 2. Click on the link 'MICR' 3. Enter more than 9 digits in the Search field | 100012300111 | The Search field Should not allow to enter more than 9 digits and should display the error message | More than 11 alphanumeric characters are allowed to enter and it does not displaying any error message | FAIL
BANK_MICRSRCH_07 | Check whether the Search field accepts less than 9 digits | 1.Open the application 2. Click on the link 'MICR' 3. Enter less than 9 digits in the Search field | 110 | The Search field Should not accept less than 9 digits and should display the error message | Less than 9 digits are allowed to enter and it does not displaying any error message | FAIL
BANK_MICRSRCH_08 | Check whether the Search field allow to enter space | 1.Open the application 2. Click on the link 'MICR' 3. Enter MICR code with space | 11000 23 | The search field should not allow to enter white space and should display an error message | The search field allow to enter white space and does not displaying any error message | FAIL

## Sheet10
IFSC-MICR CODES- All Banks
Reported To : Rugma Raghav Date : Version No : Enviornment Details :
Bug Id | Test_Id | Expected Result | Bug Description | Steps To Reproduce | Severity | Priority | Screenshot | Status
Def_Bank_01 | BANK_ALLBANK_14 | The bank 'Search ' field should not allow to enter numbers | The 'Search ' field acepts numbers and do not display any error message | 1. Open the application 2. Enter numbers in the Search field |  |  | https://drive.google.com/file/d/11VLlyl-e1EUo1pSOycdj1Rzacr-0xTn-/view?usp=share_link | NEW
Def_Bank_02 | BANK_ALLBANK_15 | The bank 'Search' field should not allow to enter any special characters and should display an error message | The 'Search ' field allow to enter special characters and do not display any error message | 1. Open the application 2. Enter special characters in the Search field |  |  | https://drive.google.com/file/d/11UlCdUtA7yYbDXWecwu3ah5mGJBD0wh7/view?usp=share_link | NEW
Def_Bank_03 | BANK_ALLBANK_16 | The searching a state that is not in the list of states should have display an error message | No error message is displayed | 1. Open the application 2. Enter some letters in the Search field |  |  | https://drive.google.com/file/d/11Rw5CCHqmG8JNMLJBwjzS2BUDKKWNaE0/view?usp=share_link | NEW
Def_Bank_04 | BANK_STATELIST_07 | The state 'Search' field should not allow to enter any numbers and should display any error message | The state 'Search ' field allow to enter numbers and do not display any error message | 1.Open the application 2. Select any bank 3. Type numbers in the Search field |  |  | https://drive.google.com/file/d/12-qODkLubXPGAwsk3_hyDJ9LqX20MLpp/view?usp=share_link | NEW
Def_Bank_05 | BANK_STATELIST_08 | The state 'Search' field should not accept any special characters and should display an yerror message | The state 'Search ' field acepts special characters and do not display any error message | 1.Open the application 2. Select any bank 3. Type special characters in the Search field |  |  | https://drive.google.com/file/d/12-5rnfyWMNIzCufYoOtwblx5akVFYJ7a/view?usp=share_link | NEW
Def_Bank_06 | BANK_STATELIST_09 | The searching a state that is not in the list of states should display an error message | No error message is displayed | 1.Open the application 2. Select any bank 3. Type a state that is not in the list of states displayed |  |  | https://drive.google.com/file/d/11wgXWOEK94dProH5ykPw9Z3LkQWbdEjZ/view?usp=share_link | NEW
Def_Bank_07 | BANK_DISTRICT_06 | The district 'Search' field should not accept any numbers and should display an error message | The district 'Search ' field allow to enter numbers and do not display any error message | 1.Open the application 2. Select any bank 3. Select a state 4. Type numbers in the Search field |  |  | https://drive.google.com/file/d/120C7Bblrx3ujOMF6uzR4CLuz2ZicXjvS/view?usp=share_link | NEW
Def_Bank_08 | BANK_DISTRICT_07 | The district 'Search' field should not accept any special characters and should display an error message | The district 'Search ' field acepts special characters and do not display any error message | 1.Open the application 2. Select any bank 3. Select a state 4. Type special characters in the Search field |  |  | https://drive.google.com/file/d/120pIwZ7XJAnekDktG_1FYV9MyQc8vdT8/view?usp=share_link | NEW
Def_Bank_09 | BANK_DISTRICT_08 | The searching of a district that is not in the list of districts should display an error message | No error message is displayed | 1.Open the application 2. Select any bank 3.Select a state 4. Type a district name that is not in the displayed list of districts |  |  | https://drive.google.com/file/d/11wXNmt0rTLjrUkll2wQZitzElzz4uyJG/view?usp=share_link | NEW
Def_Bank_10 | BANK_DISTRICT_09 | The districts should belongs to the state which already selected | Some districts are not belongs to the seleted state | 1.Open the application 2. Select any bank 3.Select a state 4. check the displayed district list |  |  | https://drive.google.com/file/d/14TOK1AKukimA83kyxSB7pe-Q5JGDT5vN/view?usp=share_link | NEW
Def_Bank_11 | BANK_BRANCH_04 | The 'Search' field should not allow to enter any numbers and should display an error message | The 'Search ' field allow to enter numbers and do not display any error message | 1.Open the application 2. Select a bank 3.Select a state 4.Select district 5. Enter numbers in the search field |  |  | https://drive.google.com/file/d/13U54eMMQJqHh25HIveAd8auyORtxMHZm/view?usp=share_link | NEW
Def_Bank_12 | BANK_BRANCH_05 | The 'Search' field should not allow to enter any special characters and should display an error message | The 'Search ' field allows to enter special characters and do not display any error message | 1.Open the application 2. Select a bank 3.Select a state 4.Select district 5. Enter special characters in the search field |  |  | https://drive.google.com/file/d/13V2lS6nF-9kK2Gnd2P4c7QB5a9G1P9fp/view?usp=share_link | NEW
Def_Bank_13 | BANK_BRANCH_06 | Searching a branch that is not in the list of branches should display an error message | No error message is displayed | 1.Open the application 2. Select a bank 3.Select a state 4.Select district 5. Enter some characters in the search field |  |  | https://drive.google.com/file/d/13SokMc6lagW8jIsYc0QX98j06VLvlJ_z/view?usp=share_link | NEW
Def_Bank_14 | BANK_BNKDTLS_04 | The zip code should be correct | The zip codes of some banks are not correct | 1. Open the application 2. Select any bank --> state --> district --> branch 3. Check the zip code |  |  | https://drive.google.com/file/d/13Zqvpmwcx96oM78PLIj_5malUKa8Pp_O/view?usp=share_link | NEW
Def_Bank_15 | BANK_BNKDTLS_05 | The address of banks should be correct | The address of some banks are not correct | 1. Open the application 2. Select any bank --> state --> district --> branch 3. Check the address |  |  | https://drive.google.com/file/d/13Zqvpmwcx96oM78PLIj_5malUKa8Pp_O/view?usp=share_link | NEW
Def_Bank_16 | BANK_RECENTS_04 | There should be an option for clearing the seach history | There is no option to clear the history | 1.OPen the application 2. Click on the 'Recents' link 3. Check for clear button |  |  | https://drive.google.com/file/d/14P7r-WWuS4NHmtS0MyReO8Xd8OwZmFaS/view?usp=share_link | NEW
Def_Bank_17 | BANK_IFSCSEARCH_04 | The IFSC Search field should not allow to enter alphabets only and should display an error message | The IFSC Search field is allowing to enter alphabets only and it does not displaying any error message | 1.Open the application 2. Click on the link 'IFSC' 3. Enter only alphabets in the Search field |  |  | https://drive.google.com/file/d/13NGLlP7Q6WvxK1hBMxtKwLtDzyJ_LGps/view?usp=share_link | NEW
Def_Bank_18 | BANK_IFSCSEARCH_05 | The IFSC search field should not allow to enter more than 11 alphanumeric characters and should display the error message | More than 11 alphanumeric characters are allowed to enter and it does not displaying any error message | 1.Open the application 2. Click on the link 'IFSC' 3. Enter more than 11 characters in the Search field |  |  | https://drive.google.com/file/d/14XvPOzfn0bpHcWvjs-2Hid7UAcJa9HWL/view?usp=share_link | NEW
Def_Bank_19 | BANK_IFSCSEARCH_06 | The IFSC search field Should not accept less than 11 alphanumeric charactersand should display the error message | Less than 11 alphanumeric characters are allowed to enter and it does not displaying any error message | 1.Open the application 2. Click on the link 'IFSC' 3. Enter less than 11 characters in the Search field |  |  | https://drive.google.com/file/d/14lctlrmviLCIN53jxeZvt7Q-tT_FFR43/view?usp=share_link | NEW
Def_Bank_20 | BANK_IFSCSEARCH_07 | The IFSC search field should not allow to enter white space and should display an error message | The search field allow to enter white space and does not displaying any error message | 1.Open the application 2. Click on the link 'IFSC' 3. Enter IFSC code with space |  |  | https://drive.google.com/file/d/14dCQLQGXJLVdj83cagfKTtMgj86uXxQv/view?usp=share_link | NEW
Def_Bank_21 | BANK_IFSCSEARCH_08 | The IFSC 'Search' field should not allow to enter any special characters and should display an error message | The IFSC 'Search ' field allow to enter special characters and it does not display any error message | 1. Open the application 2. Enter special characters in the Search field |  |  | https://drive.google.com/file/d/13Wg9-HOJnxiii8ZN-LwjtpbxhrFxfWnm/view?usp=share_link | NEW
Def_Bank_22 | BANK_IFSCSEARCH_09 | The IFSC Search field should not allow to enter numbers only and should display an error message | The IFSC Search field allows to enter only numbers and it does not displaying any error message | 1.Open the application 2. Click on the link 'IFSC' 3. Enter only numbers in the Search field |  |  | https://drive.google.com/file/d/13XXj4kp6x6hO5O2IA_2ADvdZqVebCf3c/view?usp=share_link | NEW
Def_Bank_23 | BANK_MICRSRCH_04 | The 'MICR' Search field should not allow to enter alphabets and should display an error message | The MICR Search field is allowing to enter alphabets and it does not displaying any error message | 1.Open the application 2. Click on the link 'MICR' 3. Enter alphabets in the Search field |  |  | https://drive.google.com/file/d/13RyXTvCHeBmy_ePtv7rEwfQVlpyavFC_/view?usp=share_link | NEW
Def_Bank_24 | BANK_MICRSRCH_05 | The 'Search' field should not allow to enter any special characters and should display an error message | The 'Search ' field allow to enter special characters and it does not display any error message | 1. Open the application 2. Enter special characters in the Search field |  |  | https://drive.google.com/file/d/1-ZHKbSCIISjTiapljXgcr-d3tJ0YcXqm/view?usp=share_link | NEW
Def_Bank_25 | BANK_MICRSRCH_06 | The Search field Should not allow to enter more than 9 digits and should display the error message | More than 9 digits are allowed to enter and it does not displaying any error message | 1.Open the application 2. Click on the link 'MICR' 3. Enter more than 9 digits in the Search field |  |  | https://drive.google.com/file/d/14pdnDeMZa9qtblHainZIjMVQaiIPGjYJ/view?usp=share_link | NEW
Def_Bank_26 | BANK_MICRSRCH_07 | The Search field Should not accept less than 9 digits and should display the error message | Less than 9 digits are allowed to enter and it does not displaying any error message | 1.Open the application 2. Click on the link 'MICR' 3. Enter less than 9 digits in the Search field |  |  | https://drive.google.com/file/d/13N2j0vwAFHdRtdjH6ht_SLmLKGYtGboM/view?usp=share_link | NEW
Def_Bank_27 | BANK_MICRSRCH_08 | The search field should not allow to enter white space and should display an error message | The search field allow to enter white space and does not displaying any error message | 1.Open the application 2. Click on the link 'MICR' 3. Enter MICR code with space |  |  | https://drive.google.com/file/d/14pxqp_y_KgJoIVe38ek5TX-_nr1PqtI8/view?usp=share_link | NEW

## Sheet11
DEFECT DISTRIBUTION
MODULE | DEFECT DISTRIBUTION
Splash page | 0
All Banks Page | 3
State List Page | 3
District List Page | 3
Branch List Page | 3
Bank Details | 2
Recents page | 1
IFSC Search Page | 6
MICR Search Page | 5

## Sheet12
MODULE | NO OF TESTCASES PASSED | NO OF TESTCASES FAILED | NO OF TESTCASES EXECUTED
Splash page | 6 | 0 | 6
All Banks Page | 13 | 3 | 16
State List Page | 6 | 3 | 9
District List Page | 6 | 3 | 9
Branch List Page | 3 | 3 | 6
Bank Details | 11 | 2 | 13
Recents page | 3 | 1 | 4
IFSC Search Page | 3 | 6 | 9
MICR Search Page | 3 | 5 | 8